# TUNA AND TUNA-LIKE SPECIES FISHERIES ACTION PLAN 2025-2026 (ATTSAP 2025-2026)

NATIONAL DIRECTORATE OF MARINE RESOURCES OF

MINISTRY OF FISHERIES AND MARINE RESOURCES OF ANGOLA

OCTOBER 2025

CONTENT

- INTRODUCTION	6

  - Purpose	6

  - Goal	7

- OBJECTIVES AND STRATEGIES	7

  - Objectives	7

  - Strategies and Actions (Activities)	8

ABBREVIATIONS

Abbreviation	Definition

ATTSAP MINPERMAR

SNFPA

IUU Fishing

DNRM INIPM

IPA

ICCAT

Angola Tuna and Tuna-like Species Action Plan

Ministério das Pescas e Recursos Marinhos (Ministry of Fisheries and Marine Resources )

Serviço Nacional de Fiscalização Pesqueira (National Fisheries and Aquaculture Inspection Service)

Illegal, Unreported and Unregulated Fishing

Direcção Nacional dos Recursos Marinhos (National Directorate of Marine Resources)

Instituto Nacional de Investigacao Pesqueira e Marinha (National Institute for Fisheries and Marine Research)

Instituto Nacional de Apoio a Pesca Artesanal e Aquicultura (National Institute for the Support of Artisanal Fishing and Aquaculture)

International Commission for the Conservation of Atlantic Tunas

# INTRODUCTION

Angola is bestowed with important marine resources from demersal finfish to pelagic     species including high seas or offshore resources - the Tunas. The coastal species such as Euthymus alleteratus,Sarda sarda,Scomber japonicas,Auxis thazardare found along the entire coast and being caught mainly by the artisanal and semi- industrial fishery also as bycatch of the demersal fishery. The oceanic species such   asThunnus abesus, Thunnus albacares, Thunnus alalunga, Katsuwonus pelamis and Skipjack tuna are caught by the industrial fleet using purse seines and longline (for tunas).

ICCAT members have rights and duties. The latter includes the timely submission of all statistical information and reports as established by the Compliance Committee. For Angola, some shortcomings in fulfilling its obligations have been pointed out, therefore, at institutional level, policies are being drafted and reviewed, and immediate interventions are being taken not only to meet ICCAT recommendations but also to encourage sustainable fisheries, economic maximization and resources protection against adverse fishing activities. This will require the utilization of the best available scientific information, Monitoring, Control, and Surveillance (MCS), institutional capacity building, including short courses in different fisheries domains. This includes reinforcement of sampling programs and samplers in artisanal fisheries, increase the number of onboard fisheries observers and scientific observers, to name but a few.

# Purpose

The main purpose of this Angola Tuna and Tuna-like Species Action Plan (ATTSAP 2025-2026) is to guide the Ministry of Fisheries and Marine Resources (MINPERMAR) in the short term to implementing the best tuna fisheries management practices that can bring long term benefits to the country.

# Goal

The ATTSAP 2025-2026 goal is to sustainably develop, conserve and manage the tuna fishery and to comply with ICCAT and other related international regulations.

# OBJECTIVES AND STRATEGIES

# Objectives

The main objectives of the ATTSAP 2025-2026 are outlined in the table below and are in line with the objectives of the Annual Management Measures for Marine and Continental Fisheries, Aquaculture and Salt which are under development to be implemented from the year 2025.

| Goal | Objectives |
| --- | --- |
| Sustainable Development | - Maximize and secure long-term socioeconomic revenues from the tuna fishery for the government and its people; - Promote the development of a national tuna sector; |
| Conservation and Management | - Improve control of tuna fleet activity; - Improve the system for collecting, processing, analyzing and managing tuna data; - Maintain tuna stocks at sustainable levels; |
| Institutional Governance | - Improve institutional capacity and capability for effective management of the tuna fisheries; - Comply with legal and regulatory standards including ICCAT and related international regulations and recommendations; - Mitigate risks and maintain institutional integrity. - Utilize best fisheries management practices to ensure long term social benefits to Angolan people. |

# Strategies and Actions (Activities)

| Objectives |  | Strategies | Actions | Responsible Entity | Implementing Agent | Support | Timing | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Maximize and secure long-term socioeconomic revenues from the tuna fishery for the government and its people | Develop local value adding initiatives to reduce post capture wastage in tuna landings | . Create initiatives for local utilization of bycatch and damaged fish in close collaboration with national operators | MINPERMAR | DNRM | ALL RELEVANT STAKEHOLDERS | 2025-2027 |  |
| 2 | Promote the development of a national tuna sector | Encourage the nationalization of the fleet by facilitating investments | . Convening stakeholder consultations to develop a domestic investment strategy | MINPERMAR | MINPERMAR | ALL RELEVANT STAKEHOLDERS | 2025-2027 |  |
|  |  | Review compliance shortcomings for all species | . Engage with operators to address noncompliance issues . Improve national MCS Strategy |  |  |  | Action began in 2024 and is ongoing |  |
| 3 | Improve control of tuna fleet activity | Improve domestic quota allocation, surveillance, and law enforcement | . Licensing of tuna vessels and renewal of fishing licenses; . Control of fishing revenue (from payments of certificates and licenses) . Monitoring and control of quota allocated to vessels | MINPERMAR | DNRM SNFPA | DNRM | Ongoing from January 2024 |  |

| 4 | Improve the system for collecting, processing, analyzing and managing tuna data | Encourage training for data collection to improve fishery data accuracy and efficiency. | . Organize short training programs in collaboration with the ICCAT Statistics Department (specifically to meet compliance committee requirements) . Establish data quality control and validation routine . Monitor coastal fishing activities (fishing activities, fishing methods and species caught. . Organize trainings for onboard and scientific observers | MINPERMAR | DNRM SNFPA | MINPERMAR ICCAT | November 2024 - onwards |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5 | Maintain tuna stocks at sustainable levels | Make use of the best available scientific information and a precautionary approach. | . Promote responsible fishing practices . Reinforce sampling programs and samplers in artisanal fisheries . Increase the number of onboard fisheries observers and scientific observers | MINPERMAR | DNRM IPA SNFPA | ALL RELEVANT STAKEHOLDERS | November 2024 - onwards |  |

| 6 | Improve institutional capacity and capability for effective management of the tuna fisheries; | Establish means for catch limits control in close collaboration with ICCAT and other international organizations | . Increase research capabilities through training and workshops . Enhance stakeholders collaboration . Greater control of the quota allocated by ICCAT for large tuna fishing . Collection of sport fishing data. | MINPERMAR | DNRM INIPM SNFPA IPA | ALL RELEVANT STAKEHOLDERS | January 2025 - onwards |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7 | Comply with legal and regulatory standards including ICCAT and related international regulations and recommendations; | Improve statistical data reporting mechanisms and monitor vessel activities | . Improve the export validation process for tuna and tuna-like species in line with ICCAT and international market requirements and regulations . Improve the process of issuing and validating catch certificates with a view to reducing Illegal, Unreported and Unregulated (IUU) fishing. - Work carried out in the provinces of Benguela and Namibe for periodic inspections of vessels that catch tuna - Our participation in ICCAT meetings throughout the year; | MINPERMAR | DNRM SNFPA | MINPERMAR SNFPA ICCAT | January 2025 onwards |  |
| 8 | Mitigate risks and maintain institutional integrity. | Establish a robust oversight and transparency measures for tuna and tuna-like fishery management | . Create transparent platforms for reporting catch data, enforcement actions, and compliance statistics; . Providing training for technicians, onboard and scientific observers, and fishers on best practices; Improved data collection | MINPERMAR | DNRM SNFPA | MINPERMAR SNPA ICCAT ALL RELEVANT STAKEHOLDERS | February 2025 - onwards |  |

|  |  |  | . Implement comprehensive data collection system for catch reporting and stock assessments. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 9 | Utilize best fisheries management practices to ensure long term social benefits to Angolan people. | Develop effective national regulations | . Promote community participation in management strategies to foster stewardship and accountability. . Encourage sustainable fishing practices | MINPERMAR | DNRM | ALL DIRECTORATES ALL RELEVANT STAKEHOLDERS | 2025-2026 |  |