CPC (Contracting Party/Cooperating Non-Contracting Party, Entity or Fishing Entity): Liberia

Date of submission or revision: [13/10/2025]

DEFICIENCES TO BE ADDRESSED

[List the specific issues identified by the COC] - Rec. 18-07: Compliance tables received late. - Rec. 22-03 and Rec. 19-05: Recurrent overharvest of SWO-N (2023: -115.28 t) and BUM (2023: 2023: -117.58 t). - Annual Report Word received late. - No ST03 (catch and effort) or ST09 (observer data) received. - Rec. 22-01: Task 1 for tropical species in 2023 but no corresponding periodical reports submitted. - Rec. 16-14: Unclear as to whether minimum standards of the scientific observer programme are being met, more information is required. Observer coverage <5%.

SUMMARY INTRODUCTION

[Provide a brief context on the issues and the purpose of this Action Plan] - Liberia did submit its 2023 compliance table late because of the changed in political power that brought in a new administration. - SWO-N is being harvested by the small-scale fisheries mostly as a bycatch, and Liberia has not been given any TAC. - Annual report submitted late due to the migration to IOMS. - The ST03 or ST09 was not submitted because Liberia do not have flag vessels. - Task 1 data was submitted for data collected from small-scale fisheries and submitted, but no periodical reports were submitted due to the data collection system we are using. - More information was requested as to whether the minimum standards for scientific observer program are being met. Liberia only has access agreement with private tuna companies/ vessels from third-party countries and a minimum requirement of 15% scientific observer courage is being applied.

ACTION ITEMS

[List and describe the concrete steps the CPC will implement, including where applicable the legally binding nature of the action] - Liberia is has developed a calendar of ICCAT reporting timelines and intent to submit all its reports one week before the deadline. - Liberia will follow-up with its proposal for TAC and the regular annual meeting in November 2025. To this end, SWO-N management plan has been developed and submitted to the secretariat. - Liberia is has developed a calendar of ICCAT reporting timelines and intent to submit all its reports one week before the deadline. - Liberia plan to report ST03 or ST09 zero catch starting from 2026. - To submit the corresponding periodical reports for Task 1, the small-scale landing will be analysis quarterly and report submitted start the first quarter in 2026. - Liberia has trained scientific fisheries observers ready to be placed on tuna fishing vessels when flagged to Liberia.

PLAN OF IMPLEMENTATION

[Describe how each action will be executed, responsible parties, and resource allocation] - The report calendar will be monitored by the Policy, Planning and Investment Department of the National Fisheries and Aquaculture Authority (NaFAA). The team will work with the Department of Research and Statistics to develop the annual reports. The lead person responsible for coordinating this is Austin Saye Wehye- Director of Research and Statistics, NaFAA. - The Liberia team designated for the annual meeting will follow-up on management plan. Austin Saye Wehye- Director of Research and Statistics, NaFAA to lead. - The report calendar will be monitored by the Policy, Planning and Investment Department of the National Fisheries and Aquaculture Authority (NaFAA). The team will work with the Department of Research and Statistics to develop the annual reports. The lead person responsible for coordinating this is Austin Saye Wehye- Director of Research and Statistics, NaFAA. - ST03 or ST09 zero catch starting from 2026. Nasi T. Broh, Associate Director of Statistics (NaFAA) is the responsible person. - Task 1 corresponding periodic reports will be collated and submitted quarterly starting 2026. Nasi T. Broh, Associate Director of Statistics (NaFAA) is the responsible person. - Scientific observers to be placed on Liberian flag tuna vessels.

TIMELINE / INCREMENTAL BENCHMARKS FOR COMPLETION

[Outline the schedule with milestones for each corrective action, including where applicable dates that planned actions will enter into effect] - COC draft report will be prepared one month to the deadline and submitted two weeks to the deadline. - Liberia to follow-up on the management plan at the 29th regular meeting of the commission. Liberia to be allocated TAC for SWO-N. - Draft report will be prepared one month to the deadline and submitted two weeks to the deadline. - Start submitting zero catch by 2026 - Start submitting quarterly report by 2026. - When Liberia flag vessels in 2026

EXPECTED IMPROVEMENTS / OUTCOMES IN THE NEXT YEAR

[Specify measurable improvements expected as a result of the plan] - Liberia to submit its COC report before the deadline. - TAC allocated to Liberia and reduction in the over-catch. - Annual reports submitted be the deadlines. - ST03 or ST09 report submitted by 2026. - Quarterly reports submitted- 2026. - Flag at least two industrial tuna vessels and carryout 100% scientific observer courage.

DIFFICULTIES ENCOUNTERED / ALTERNATIVE ACTIONS TAKEN

[Describe any challenges faced during implementation and adjustments made] This will be documented when implementing these actions.

CONCLUDING SUMMARY

[Summarise the overall approach and commitment to resolving the deficiencies] This plan will be jointly implemented by the Research and Statistics Department and the Policy, Planning, and Investment Department of the National Fisheries and Aquaculture Authority (NaFAA) of Liberia. In accordance with the implementation framework outlined in the plan, both departments will collaborate to ensure effective coordination, data collection, and monitoring of progress. To maintain accountability and facilitate timely review, annual reports will be prepared and submitted to the Secretariat at least two weeks prior to the official reporting deadline. This timeline allows sufficient opportunity to review the reports, address any comments or feedback, and make necessary revisions if applicable. The process aims to promote transparency, continuous improvement, and alignment with NaFAA’s broader strategic objectives.

LIST OF APPENDICES AND ATTACHMENTS [If applicable, list appendices or attachments with additional information, such as copies or excerpts of relevant laws, regulations, administrative actions, procedures, and policies] - Chapter 11 of the Fisheries and Aquaculture Management and Development Law of 2019.