CPC (Contracting Party/Cooperating Non-Contracting Party, Entity or Fishing Entity): TRINIDAD AND TOBAGO

Date of submission or revision: [10/10/2025]

DEFICIENCES TO BE ADDRESSED

- Implementation of scientific observer program (Rec. 16-14); - Turtle by-catch requirements (Rec. 22-12); and - Recurring late reporting.

SUMMARY INTRODUCTION

[Provide a brief context on the issues and the purpose of this Action Plan] The enactment of new fisheries management legislation that provides the framework for integrating international obligations into national law is necessary and accorded high priority. Currently, most fisheries conservation and management efforts in Trinidad and Tobago, including implementation of a scientific observer programme (Rec. 16-14) and turtle by-catch requirements (Rec. 22-12), rely on voluntary compliance of stakeholders. There is also the need to strengthen the administrative and institutional framework for fisheries conservation and management, including re-establishment of the fisheries monitoring, control, surveillance and enforcement capability and strengthening the existing fisheries scientific research capability. This Action Plan (2025 to 2030) is intended to address the legislative, administrative and other institutional constraints necessary to implement ICCAT’s conservation and management measures in general, and more specifically a scientific observer programme (Rec 16-14), turtle by-catch requirements (Rec. 22-12) and timely and comprehensive reporting.

ACTION ITEMS

[List and describe the concrete steps the CPC will implement, including where applicable the legally binding nature of the action] - Enact new fisheries management legislation which provides the framework for incorporating ICCAT’s conservation and management measures into national law and develop priority regulations; - Continue implementation of the GEF-Funded Project - Strategies, Technologies and Social Solutions To Manage Bycatch in Tropical Large marine Ecosystem Fisheries (REBYC-III CLME+) with focus on the artisanal gillnet fleet and the non-artisanal longline fleet; - Strengthen the administrative and institutional capacity for fisheries conservation and management in Trinidad and Tobago to facilitate the implementation of new fisheries management legislation.

PLAN OF IMPLEMENTATION

[Describe how each action will be executed, responsible parties, and resource allocation] - Enact new fisheries management legislation which provides the framework for incorporating ICCAT’s conservation and management measures into national law and develop priority regulations; - Update the Fisheries Management Bill - FMB (based on stakeholder feedback at and following the November 2023 consultations), - Re-submit the updated FMB to the Cabinet; - Lay the updated FMB in Parliament; - Pass new fisheries management legislation; - Update the national bycatch management plan*⇞; - Develop a National Plan of Action for addressing Abandoned, Lost and Otherwise Discarded Fishing Gear (NPOA-ALDFG)*⇞; - Endorsement of the bycatch management plan by the Minister and Cabinet; - Endorsement of the NPOA-ALDGF by the Minister and Cabinet; - Develop regulations for the management of bycatch*; - Develop regulations for the management of abandoned, lost and discarded fishing gear*; - Update regulations for, monitoring, control and surveillance and administrative (licensing and registration) procedures; - Develop regulations for establishment of a Trinidad and Tobago Observer Programme (TTOP). Responsible parties : Ministers with responsibility for fisheries and legal affairs and their respective technical staff; the Secretary with responsibility for fisheries in the Tobago House of Assembly and the respective technical staff, the Cabinet and the Parliament of Trinidad and Tobago; Consultants hired to draft policy for the regulations, the Legal Drafting Department of the Office of the Attorney General and Ministry of Legal Affairs; Ministry of Finance; The Project Management Unit for REBYC-III CLME+ and EAF4SG Projects; The University of the West Indies (St Augustine). Resource allocation: the Recurrent Programme Budget of the respective Government agencies; Global Environment Facility (GEF) Projects (a) Strategies, Technologies and Social Solutions To Manage Bycatch in Tropical Large marine Ecosystem Fisheries (REBYC-III CLME+)*; (b) Enhancing capacity for the adoption and implementation of Ecosystem Approach to Fisheries (EAF) in the shrimp and groundfish fisheries of the North Brazil Shelf Large Marine Ecosystem (EAF4SG)⇞. - Continue implementation of the GEF-Funded Project - Strategies, Technologies and Social Solutions To Manage Bycatch in Tropical Large marine Ecosystem Fisheries (REBYC-III CLME+);- project commenced in January 2024 and scheduled to end in 2027 - Improve data collection systems for the multi-gear artisanal fleet and non-artisanal longline fleet to capture data and information on gear interactions with endangered, threatened, vulnerable and protected species; - Implement net LED illumination experiments to test the efficacy of lights in mitigating sea turtle bycatch in gillnets and determine the socio-economic impacts; - Promote pelagic line fishing as an alternative to gillnet fishing; - Explore the rearing of bait as a business enterprise in support of live-bait fishing using pelagic lines; - Determine the characteristics of the non-artisanal longline fleet; - Test the efficacy of different hook types [circle hooks (12.0) vs tuna-J hooks (12.0)]; and hook sizes [circle hooks (12.0) vs circle hooks (16.0)] in mitigating sea turtle bycatch in the non-artisanal longline fleet - associated data collection at sea will serve as a pilot observer programme; - Conduct Marine Megafauna Survey to characterize the megafauna bycatch associated with the artisanal multi-gear and non-artisanal longline fleets ( including details on bycatch fate, temporal trends and spatial hotspots, the causes of bycatch and stakeholder views on possible solutions to manage megafauna bycatch, enhance the likelihood of survival and reduce post-release mortality); - Build capacity of stakeholders in procedures and use of tools for improving post-release survival of marine turtles in the artisanal gillnet and non-artisanal longline fleets. - Pilot an electronic monitoring (EM) system on the artisanal gillnet fleet and the non-artisanal longline fleet; - Draft recommendations/guidance to strengthen the legal/regulatory framework for bycatch management; - Consult with fisheries stakeholders on the draft bycatch management recommendations/measures. Responsible parties: Fisheries Division; Ecolibrium Inc;, the University of the West Indies - St Augustine (Faculty of Food and Agriculture; Faculty of Science and Technology); National Consultants; National Technical Coordinator; Lead Technical Advisers; NGO - Future Fishers; National Sea Turtle Task Force; The Project Management Unit for REBYC-III CLME+ and EAF4SG Projects; The University of the West Indies (St Augustine). Resource allocation: the GEF-funded REBYC-III CLME+ and EAF4SG Projects; Fisheries Division Recurrent Budget Programme; Ecolibrium Inc..; Department of Marine Resources and Fisheries - Tobago House of Assembly Recurrent Budget Programme; TTO National Environmental Fund (Green Fund). - Strengthen the administrative and institutional capacity for fisheries conservation and management in Trinidad and Tobago to facilitate the implementation of new fisheries management legislation. - Secure funding and technical assistance for the conduct of an institutional review of the fisheries administrations in Trinidad and in Tobago with recommendations to facilitate implementation of new fisheries management legislation; - Recruit technical staff on the Fisheries Division’s establishment; - Recruit twenty-three monitoring, control, surveillance and enforcement (MCS&E) staff on contract; - Recruit two at-sea data collectors*; - Train new technical staff; - Train MCS&E staff; - Train at-sea data collectors*; - Deploy technical staff in priority areas – including areas for meeting ICCAT obligations; - Deploy MCS&E staff to implement new fisheries management legislation; - Deploy at-sea data collectors to collect data for gear experiments*; - Build awareness of senior policy-makers in the Ministry with responsibility for fisheries on ICCAT matters; - Commence implementation of recommendations from the institutional review at 3(a). Responsible parties: Fisheries Division; the Ministers with responsibility for fisheries and finance; the Cabinet and its Finance and General Purpose Committee; the Human Resource Management Department of the Ministry with responsibility for Fisheries; the Office of the Chief Personnel Officer, the Service Commissions Department;, the Ministry with responsibility for public administration; The Project Management Unit for REBYC-III CLME+ and EAF4SG Projects; The University of the West Indies (St Augustine). Resource allocation (c. and d.): the Recurrent Programme Budget of the Fisheries Division, likely donor-funding and technical assistance for conduct of institutional review; the GEF-funded REBYC-III CLME+ Project.

TIMELINE / INCREMENTAL BENCHMARKS FOR COMPLETION

[Outline the schedule with milestones for each corrective action, including where applicable dates that planned actions will enter into effect] - Enact new fisheries management legislation which provides the framework for incorporating ICCAT’s conservation and management measures into national law and develop priority regulations; - Fisheries Management Bill (FMB) updated (Oct. 2025); - Updated FMB re-submitted to the Cabinet (Nov. 2025); - Updated FMB laid in Parliament (Mar. 2026); - New fisheries management legislation enacted (Nov. 2026); - National bycatch management plan updated (Jun. 2026)*; - NPOA-ALDFG developed- (Dec. 2026)*; - National bycatch management plan endorsed by the Minister (Sep. 2026) and by the Cabinet (Dec. 2026); - NPOA-ALDGF endorsed by the Minister (Mar. 2027) and by the Cabinet (Jun. 2027); - Regulations developed for the management of bycatch (Dec. 2027)*; - Regulations developed for the management of abandoned, lost and discarded fishing gear (Dec. 2027)*; - Regulations updated for monitoring, control and surveillance and administrative (licensing and registration) procedures (Jun. 2027); - Regulations developed for establishment of a Trinidad and Tobago Observer Programme (TTOP) - (Jun. 2027). - Continue implementation of the GEF-Funded Project - Strategies, Technologies and Social Solutions To Manage Bycatch in Tropical Large marine Ecosystem Fisheries (REBYC-III CLME+);- project commenced in January 2024 and scheduled to end in 2027 - Data collection systems improved and implemented for the multi-gear artisanal fleet and non-artisanal longline fleet to capture data and information on gear interactions with endangered, threatened, vulnerable and protected species: updated data collection form for artisanal multi-gear fleet (Dec. 2026); eLogbook system implemented for the non-artisanal longline fleet (Jan 2024); training of captains in use of eLogbook system (Ongoing); - Net LED illumination experiments implemented to test the efficacy of lights in mitigating sea turtle bycatch in gillnets and determine the socio-economic impacts (Dec. 2026); preliminary technical report produced (Sep. 2025) and final technical report produced (Dec. 2026); - Pelagic line fishing promoted as an alternative to gillnet fishing (Ongoing); - The rearing of bait as a business enterprise is explored in support of live-bait fishing using pelagic lines (Oct. 2027) and the final report with recommendations is produced (Dec. 2027); - The non-artisanal longline fleet is surveyed (Mar. 2026); final technical report produced (Jun. 2026); - The efficacy of different hook types and hook sizes in mitigating sea turtle bycatch in the non-artisanal longline fleet is tested and pilot observer programme implemented (Sep. 2026); final technical report on gear testing with recommendations produced (Mar. 2027) - Marine Megafauna Survey conducted (Dec. 2025); final technical report with recommendations produced (Mar. 2026); - Stakeholders’ capacity strengthened in procedures and use of tools for improving post-release survival of marine turtles in the artisanal gillnet and non-artisanal longline fleets (Dec. 2026); - Electronic monitoring (EM) system piloted on the artisanal gillnet fleet (Oct. 2027) and the non-artisanal longline fleet (Oct. 2027); - Recommendations/guidelines drafted to strengthen the legal/regulatory framework for bycatch management (Dec. 2027); - Fisheries stakeholders consulted on the draft bycatch management recommendations/measures (Dec. 2027). - Strengthen the administrative and institutional capacity for fisheries conservation and management in Trinidad and Tobago to facilitate the implementation of new fisheries management legislation. - Funding and technical assistance obtained for the conduct of an institutional review of the fisheries administrations in Trinidad and in Tobago (Dec 2026); institutional review conducted (Dec. 2027); final report with recommendations produced (Jun. 2028); ICCAT assistance to be sought; - Technical staff on the Fisheries Division’s establishment recruited: vacant positions advertised and applications received (Sep. 2025); interviews conducted (Dec. 2026); technical staff recruited (Jun. 2027); - Recruit twenty-three monitoring, control, surveillance and enforcement (MCS&E) staff on contract: Note submitted to the Cabinet for consideration of hire of staff (May 2025); advertise positions and receive applications, shortlist applicants, conduct interviews and hire staff (contingent on the Cabinet’s decision); - Two at-sea data collectors recruited*: suitable candidates identified (Dec 2025); candidates trained in species identification, data collection protocols and sampling procedures (Mar. 2026); data collectors selected based on training assessment (Mar. 2026); data collectors trained in safety and survival at sea (Apr. 2026); - New technical staff trained in: the roles and functions of the Fisheries Division; national fisheries management legislation; international obligations; fishing gear and methods; fish species identification; data collection procedures; fisheries assessment and management – (Ongoing from the time of recruitment); ICCAT assistance to be sought; - MCS&E staff trained in: the roles and functions of the Fisheries Division; national fisheries management legislation; international obligations; fishing gear and methods; fish species identification; data collection procedures; operational mechanisms (e.g. electronic monitoring systems, VMS, SEW monitoring, fisheries conservation and management measures); strengthening networking with other governmental regulatory agencies; precept training; firearm use, safety at sea; medical first aid; conflict resolution; port inspection procedures - (Ongoing from the time of recruitment); ICCAT assistance to be sought; - Technical staff deployed in priority areas – including areas for meeting ICCAT obligations (June 2027); - MCS&E staff deployed to implement new fisheries management legislation (contingent on the Cabinet’s decision); - At-sea data collectors deployed to collect data for gear experiments* (May 2026); - Senior policy-makers in the Ministry with responsibility for fisheries more aware of ICCAT matters, responsibilities and obligations - (Ongoing) - Implementation of recommendations from the institutional review at 3(a) commenced (Jan. 2029).

EXPECTED IMPROVEMENTS / OUTCOMES IN THE NEXT YEAR

[Specify measurable improvements expected as a result of the plan] By November 2026, the following is anticipated to be achieved: - New fisheries management legislation enacted; - National bycatch management plan updated and endorsed by the Minister; - Pilot observer programme implemented; - Marine Megafauna Survey report with recommendations produced.

DIFFICULTIES ENCOUNTERED / ALTERNATIVE ACTIONS TAKEN

[Describe any challenges faced during implementation and adjustments made]

CONCLUDING SUMMARY

[Summarise the overall approach and commitment to resolving the deficiencies] Trinidad and Tobago recognizes that its shortcomings in implementation of ICCAT’s conservation and management measures and reporting obligations relate primarily to its outdated fisheries management legislative framework and limitations in its administrative and institutional capacity, including human resource constraints. As such, the Action Plan prioritizes addressing these components. Specifically, with reference to the implementation of bycatch management measures, the country is participating in the REBYC-III CLME+ Project to obtain the requisite technical and financial support to draft and implement bycatch management regulations.

LIST OF APPENDICES AND ATTACHMENTS [If applicable, list appendices or attachments with additional information, such as copies or excerpts of relevant laws, regulations, administrative actions, procedures, and policies] - Fisheries Management Bill (October 2023 version) – currently being updated following November 2023 stakeholder consultations; - Updated data collection form for the artisanal multi-gear fleets; - Trip and Exportation Report Form for the non-artisanal longline fleet; - REBYC-III CLME+ Project Document – signed by TTO; - Pelagic Longline Survey Form; - Marine megafauna study proposal; - Marine megafuana survey instrument; - Draft Trinidad and Tobago By-catch Management Plan; - Draft report “Promoting Sustainable Fishing Through Reduction of Megafauna Bycatch in Trinidad” Ecolibrium Inc.; - Sample Commercial Fishing Authorization (CFA); - Draft Terms of Reference for Review of Institutions Responsible for Fisheries Conservation and Management and Recommendations to Effectively Facilitate Implementation of New Fisheries Management Legislation; - Draft Request for Proposals (RFP) for Electronic Monitoring (EM) System on the non-artisanal longline fleet.