CPC: St. Vincent and the Grenadines

Date of submission or revision: [17/10/2025]

DEFICIENCES TO BE ADDRESSED

Recurring issue that requires an action plan: Inability to identify marlin species (related to the recurrent overharvest of WHM).

SUMMARY INTRODUCTION

- Inability to identify marlin species and potential recurrent overharvest of white marlin.. Due to the recurrent overharvest of WHM, the Fisheries Services initiated a rapid investigation to ascertain the true nature of the issue. This rapid investigation has revealed that data recorders are not familiar with the marlin species; therefore, the marlin species identified in the landings are inaccurate. It is highly likely that the species recorded as WHM is not always WHM. Presently, the local human resource available to conduct identification of ICCAT species is limited. Therefore, there is an urgent need for persons to be trained in the identification of billfishes and other ICCAT species. If it has been determined that there has been a recurrent overharvest of WHM, then a second phase of actions will be implemented.

ACTION ITEMS

Phase one - Organise training in the identification of fish species. - Investigate the identity of billfish being landed to validate if the billfish species are being identified properly. - Draft recommendation along with other CPCs to address the matter of WHM overharvest. Phase two (if overharvest of WHM determined after capacity building in Phase one has been executed) - Consult with fishers to conduct an in depth evaluation of the importance of WHM to their livelihoods. - Utilise the information collected in Phase two, Activity 1 to request increased landing limit as appropriate.

PLAN OF IMPLEMENTATION

[Describe how each action will be executed, responsible parties, and resource allocation] - St. Vincent and the Grenadines, Barbados and Trinidad and Tobago will work on draft recommendation to address the matter of overharvest of WHM in the Caribbean. - Conduct marlin species identification training in 2026 with persons responsible for recording the landing of marlins. The source of funding for this project has not been identified yet. - Investigate the identity of marlins landed to validate if the species are being identified properly. To be done in 2026. Field visits to be covered by project funding or the internal budget of the Ministry of Agriculture, Forestry, Fisheries, Rural Transformation, Industry and Labour. - The Fisheries Services will conduct a consultation with fishers in 2026 to re-evaluate the importance of marlins to their livelihoods. This may require at least six consultations/field visits. A project to obtain funding has not been identified in this the initial stage. Presently, the recurrent budget of the Ministry of Agriculture, Forestry, Fisheries, Rural Transformation, Industry and Labour can be utilized to conduct consultations/field visits.

TIMELINE / INCREMENTAL BENCHMARKS FOR COMPLETION

[Outline the schedule with milestones for each corrective action, including where applicable dates that planned actions will enter into effect] - Before annual Commission meeting-Draft recommendation on blue marlin and white marlin/roundscale spearfish sent to ICCAT. - 2026. Conduct training on the identification of marlin and other ICCAT species. - 2026- Conduct investigation on marlins being landed to validate if the species are being identified properly. - 2026- Conduct a consultation with fishers to re-evaluate the importance of marlins to their livelihoods.

EXPECTED IMPROVEMENTS / OUTCOMES IN THE NEXT YEAR

- Improved identification of marlin species. - Increased quotas for St. Vincent and the Grenadines from the 355t landing limit.

DIFFICULTIES ENCOUNTERED / ALTERNATIVE ACTIONS TAKEN

[Describe any challenges faced during implementation and adjustments made] - The proposed draft recommendation to address the matter of WHM overharvest relies on the consensus of other parties for it to be accepted. Therefore it cannot be guaranteed that changes will be made to the landing limits.

CONCLUDING SUMMARY

[Summarise the overall approach and commitment to resolving the deficiencies] The main issue that requires addressing with a plan of action is the overharvest of WHM. The other issues are more of an administrative nature that has to do with inadequate staffing to complete the various activities of the Fisheries Services before deadlines. There is an issue if potential misidentification of marlin species that needs resolution. It is difficult for fishers in St. Vincent and the Grenadines to reduce their harvesting marlins because they are very important for their livelihoods. St. Vincent and the Grenadines will utilize an approach of requesting an increase in landing limit from the overall landing limit of 355t. This will aid in maintaining sustainable exploitation, as a request that will increase the landing limit above 355t is not being proposed.

LIST OF APPENDICES AND ATTACHMENTS