## Sheet1
PWG_412/2018
FOLLOW UP OF THE ICCAT PERFORMANCE REVIEW - PWG
Chapter | Recommendations | LEAD | Timeframe | Proposed Next Steps | Observations/ Comments | Action to be taken, or already taken; - INPUT FROM 2018 IMM - | Completion status following annual meeting | Comments
Data Collection and Sharing | 6. The Panel recommends that a mechanism be found to allow minor occasional harvesters without allocations to report their catches without being subject to sanctions. | COC
| 6bis. The Panel concludes that ICCAT scores well in terms of agreed forms and protocols for data collection but, while progress has been made, more needs to be done particularly for bycatch species and discards. | SCRS | [5 empty] | See comments SCRS_BIL WG
Port State Measures | 67. Amends Rec 12-07 to ensure more consistency with the PSM Agreement, in particular by including definitions and requiring CPCs to impose key port State measures such as denial or use of port in certain scenarios. | PWG | S | Refer to PWG for consideration and appropriate action. |  | IMM discussed at the April 2018 meeting; Agenda Item 5.d.; Proposal is still under consideration.
| 68. Closely follows IOTC’s efforts to enhance effective implementation of its port State measures through, inter alia, its e-PSM system, and, where appropriate, adopt similar efforts within ICCAT. | PWG | S/M | Refer to Online Reporting Working Group for analysis. | South Africa is already sending Port Inpsection Reports to ICCAT through ePSM. IOTC have updated the referential tables to include the necessary ICCAT codes/references etc. | The Working Group on Online Reporting agreed that exploration of developments in other fora would be appropriate before any decisions were taken, such as the forthcoming FAO workshop which would also give consideration to Port State Measure implementation or the next Kobe meeting. The WG on Online Reporting agreed to await the outcomes of this workshop and to revert to this issue intersessionally during the coming year.
| 69. Make more efforts to assess substantive compliance with its port State measures and to specify consequences for non-compliance. | COC | S | Refer to PWG to review implementation and determine any technical improvements that might be needed. Refer to COC to consider any issues non-compliance and recommend appropriate actions. |  | IMM considered amendments to Rec. 12-07 that are intended to improve the Commission's review of compliance with the measure. PWG will be able to use any recommendations coming from the COC in order to make technical improvements in that area.
Integrated MCS Measures | 70. Gives priority to adopting a modern HSBI scheme - through a Recommendation and not a Resolution - that extends to all key ICCAT fisheries as such, but can be applied in practice to selected fisheries according to the COC’s compliance priorities. | PWG | M | Refer to the PWG as work on this matter is ongoing. |  | Adopting a modern high seas boarding inspection scheme remains open, and text remains on the table to facilate those dicussions. Discussed at the April 2018 IMM; Agenda Item 5c; A proposal was accepted for a voluntary measure that promotes the concept of at-sea inspector exchanges.
| 71. Evaluates the need and appropriateness of further expanding coverage by national and non-national on-board observers for fishing and fishing activities. | PWG | M | Refer to PWG for consideration and also the Panels as observer program requirements can be and some have been agreed as part of management measures for specific fisheries. | SCRS evaluation of current observer program requirements is pending due to lack of reporting. | Expansion of observer coverage by ICCAT remains under consideration. CPC's concerned are also requested to report on their observer coverage by way of their annual report. Request the Compliance Committee to confirm whether CPCs are complying with the requirements contained in Rec. 16-14.
| 72. Considers expanding VMS coverage, adopting uniform standards, specifications and procedures, and gradually transforming its VMS system into a fully centralized VMS. | PWG | S | Refer to PWG for consideration as Rec. 14-07 must be reviewed per para 6 in 2017. Also refer to the Panels as VMS requirements can be and some have been agreed as part of management measures for specific fisheries. |  | Discussed at the April 2018 IMM Meeting; Agenda item 5a; A proposal was introduced and discussions are ongoing.
| 73. Works towards replacing all SDPs with electronic CDPs that are harmonized among tuna RFMOs where appropriate - in particular for bigeye tuna - while taking account of the envisaged FAO Voluntary Guidelines on Catch Documentation Schemes. | PWG | M | Refer to PWG for further analysis. |  | Discussed at the April 2018 IMM Meeting; Agenda item 4b; IMM requested that the Secretariat in time for the 2018 Commission annual meeting compile information to inform Commission consideration of the risks posed to ICCAT stocks by IUU activities and/or other potential threats and possible ways to address any such threats, such as the use of Catch Documentation Schemes.
| 74. Considers, in the interest of transparency, incorporating all measures relating to distinct MCS measures - in particular transhipment and on-board observers - in one single ICCAT Recommendation, so that CPCs have only one reference document to consult. | PWG | M | Refer to PWG for assessment of the pros and cons of this approach. |  | Because of the significant administrative burden of this exercise, it is suggested to maintain separate recommendations, to systematically delete obsolete measures to refresh references in the remaining ones.
Cooperative Mechanisms to Detect and Deter Non- Compliance | 79. The Panel recommends that independent information from the fisheries, through inspections at sea and in port, and through effective observer programmes, are made available to the COC, in order for the COC to conduct an effective compliance assessment. | PWG | M | Refer to PWG to consider if there are technical reasons for implementation failures and how to address them if so; Refer to COC to consider extent of any non-compliance and recommend appropriate action. | Some independent information is available to COC due to ICCAT requirements but implementation and reporting problems exist in some cases that can limit evaluation of compliance by CPCs. | Observer and inspection reports are made available to the Commission and subsidiary bodies. Discussed at the April 2018 IMM Meeting; Agenda item 5d; A proposal was introduced and discussions are ongoing.
Market-Related Measures | 84. The Panel, noting Rec. 12-09, commends ICCAT for its initiatives in this area and recommends that catch documents, preferably electronic, be introduced for bigeye and swordfish species. | PWG | M | See Recommendation 73 above for proposed action. |  | Discussed at the April 2018 IMM Meeting; Agenda item 4b; IMM requested that the Secretariat in time for the 2018 Commission annual meeting compile information to inform Commission consideration of the risks posed to ICCAT stocks by IUU activities and/or other potential threats and possible ways to address any such threats, such as the use of Catch Documentation Schemes.
Reporting Requirements | 85. The Panel recommends that ICCAT, though its Panels 1 to 4, should undertake an overall review of the current reporting requirements, on a stock by stock basis, both in relation to Task I and Task II data contained in the myriad of recommendations, in order to establish whether the reporting obligations in question could be reduced or simplified. | PWG | M | Refer to PWG to undertake this review and present its findings and suggestions to the Panels for their approval. | Such a review will involve many recommendations including proposals developed by virtually all the Panels. PWG is well placed to take a comprehensive look at all these measures. SCRS and the Secretariat could also provide support for this work where appropriate. The online reporting group has also requested that requirements be streamlined and simplified. | Request that, after receiving input from the Online Reporting Working Group by 30 June, the Secretariat circulate to Subsidiary Bodies a list of reporting requirements and how they are used. The Panel can consider which of these reporting requirements is redundant or unnecessary.
| 87. The Panel recommends that ICCAT consider introducing a provision in new recommendations, whereby the introduction of new reporting requirements would only become effective after a 9 to 12 month period has elapsed. This would assist Developing States to adapt to new requirements. This is particularly relevant where the volume and/or nature of the reporting have changed significantly. The difficulties Developing States encounter in introducing new administrative/reporting requirements at short notice, is well documented in the compliance context. The option for Developed CPCs to apply immediately the new reporting requirements may of course be maintained, if those CPCs consider it opportune. | COM - to be considered by all bodies | S | Refer to all ICCAT bodies that can recommend binding reporting requirements for consideration when developing such recommendations. Commission to coordinate action among the bodies. |  | A global standard may not be appropriate. Application should be handled on a case-by-case basis rather than a blanket coverage for all recommendations
Confidentiality | 97. Considers further improvements, for instance by making more of its data and documents publicly available and - as regards documents - explaining the reasons for classifying certain documents as confidential. | COM - referred to PWG | M | Refer the issue to the Commission / PWG and SCRS to begin a review of ICCAT's rules on confidentiality and their application and needed adjustments can be identified, if any. |  | There is merit in the SCRS reviewing data confidentiality rules and consider processes within other RFMOs. The PWG should consider this recommendation at the 2018 annual meeting.
| 98. Conducts a review of its Rules and Procedures on Data Confidentiality as envisaged in its paragraph 33, taking into account the need for harmonization among tuna RFMOs consistent with Rec KIII-1. As part of this review, it should adopt an ICCAT’s Information Security Policy (ISP), where appropriate. | PWG | M | Refer the issue to the PWG and SCRS to begin a review of ICCAT's rules on confidentiality and their application and needed adjustments can be identified, if any. |  | There is merit in an external review of the Secretariat's current security policies. The PWG should consider this recommendation at the 2018 annual meeting.
Special requirements of developing States | 110 a) Urges developing CPCs to make the necessary efforts to assist the ICCAT Secretariat in identifying their capacity building needs; | PWG | S | Refer to the PWG where work is already underway through the Port Inspection Experts Group (established per Rec. 16-18). |  | The Port Inspection Expert Group had developed a two tier questionnaire which has been circulated to all CPCs and responses have been requested by 30APR. Discussed at the April 2018 IMM Meeting; Agenda item 5d; A proposal was introduced and discussions are ongoing.
| 110 b) Closely coordinates the operation of Rec 14-08 with existing and future capacity building initiatives undertaken by other intergovernmental bodies. | PWG | S/M | Refer to the PWG where work is already underway through the Port Inspection Experts Group (established per Rec. 16-18). |  | The Port Inspection Expert Group invited an expert (funded by ABNJ) to its meeting last October, in order to better learn of initiatives and developments in that RFMO. Discussed at the April 2018 IMM Meeting; Agenda item 5d; A proposal was introduced and discussions are ongoing.