## Sayfa1
STF_212A/18
STATUS UPDATE OF CONCLUSIONS OF THE AD HOC WG ON FOLLOW UP OF THE SECOND ICCAT PERFORMANCE REVIEW
Performance Review Feedback
Not started/little progress
Progress/requiring additional work
Completed/significant progress made
Chapter | Recommendations | LEAD | Timeframe | Proposed Next Steps | Observations / Comments | Actions to be taken, or already taken | Completion status following Annual meeting | Comments
ICCAT Basic Texts | 3. The Panel recommends that ICCAT make consolidated versions of individual basic ICCAT instruments available on the ICCAT website. | STACFAD | S | Refer this and related recommendations, in particular those concerning revisions to ICCAT's Rules of Procedure and observer rules, to STACFAD for consideration and apropriate action, including providing advice to the Commission on the timing for posting of these documents on the ICCAT website. | Mail voting procedures (Rule 9) need particular attention. In addition, several other recommendations from the Performance Review relate to revisions to ICCAT's Rules of Procedure and should be considered as a package by STACFAD. | The 6th revision of ICCAT Basic Texts and updated version of Staff Rules & Regulations were posted on ICCAT website following the 2017 Commission meeting. The Basic Texts reflects further changes to Rule 9 of the Rules of Procedure concerning mail voting. A revised version of the Basic Texts will need to be published in line with the outcomes of the Convention amendment process. The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Progress/requires additional work.
Decision Making | 92. Reviews its Rules of Procedure, among other things to integrate its 2011 Deadlines and Guidelines for the Submission of Draft Proposals, Rec. 03-20 and Res. 94-06.
Transparency | 94. Considers codifying its practices on participation by NGOs - which are consistent with international minimum standards and comparable to those of other tuna RFMOs - by amending the ICCAT Observer Guidelines and Criteria or the ICCAT Rules of Procedure. |  | M |  |  | No action has yet to be taken in regard to review of the policy on NGOs’ attendance at ICCAT meetings. The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Not started/little progress
| 95. Considers requiring Contracting Parties that object to an application by an NGO for Observer Status with ICCAT to provide their reasons in writing. |  | S
| 96. Considers that closing formal ICCAT meetings to observers requires an explicit and reasoned decision supported by a simple majority of Contracting Parties. |  | S/M
Reporting Requirements | 87. The Panel recommends that ICCAT consider introducing a provision in new recommendations, whereby the introduction of new reporting requirements would only become effective after a 9 to 12 month period has elapsed. This would assist Developing States to adapt to new requirements. This is particularly relevant where the volume and/or nature of the reporting have changed significantly. The difficulties Developing States encounter in introducing new administrative/reporting requirements at short notice, is well documented in the compliance context. The option for Developed CPCs to apply immediately the new reporting requirements may of course be maintained, if those CPCs consider it opportune. | COM - to be considered by all bodies | S | Refer to all ICCAT bodies that can recommend binding reporting requirements for consideration when developing such recommendations. Commission to coordinate action among the bodies. |  | Discussed at the April 2018 IMM. A global standard (application) may not be appropriate and could be handled on a case-by-case basis rather than a blanket coverage for all recommendations. The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Not started/little progress
| 86. The Panel recommends that before the adoption of each new recommendation, there should be an assessment as to the likely impact on the Secretariat’s workload that its implementation implies. | STACFAD |  | Refer to STACFAD to develop options for implementing this recommendation. | Option 1 - The Secretariat with guidance from the STACFAD shall develop a "cover note" template that would be embedded in a new recommendation with a view to indicating inter alia, the timeframe for implementation, the resources it will require to achieve implementation and the potential impact on the Secretariat's workload. | The STACFAD needs to consider this recommendation at the 2018 Annual meeting.
Decision Making | 89. Revises the opt-out procedures included in Res. 12-11 and the most recent text of the Amended ICCAT Convention to bring them more in line with modern opt- out procedures used by RFMOs that have been recently established or that have recently amended their constitutive instruments. | STACFAD | M - re/ Res. 12-11; NOAC - re/ Conv. Amendment opt-out provisions | Refer recommendation to revise Res. 12-11 to STACFAD for consideration | The opt-out procedures developed by the CWG was a topic of intense negotiation. No further actions are considered necessary until such time the Commission adopts such procedures. | The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Not started/little progress
Participation and Capacity Building | 108. Considers pursuing capacity building initiatives to strengthen participation in ICCAT meetings in a broader sense - including for key ICCAT positions - for instance by human resource development (e.g. by training courses on participation in, and chairing of, intergovernmental negotiations and bodies). | STACFAD | S/M | Refer to STACFAD to consider and advise on this issue. | Option 1 = Organization of regional workshops / consultation meetings by Commission Chair to provide inputs to formulize an overarching strategy built on needs of Developing CPCs. Option 2 = To this end, SWGSM Terms of Reference could be amended to incorporate focused actions to be undertaken by SWGSM towards identification of specific mechanisms and strategies for streamlining capacity building and assistance works in ICCAT. Option 3 = The Secretariat with guidance from the STACFAD shall develop a Terms of Reference for establishment of an ad hoc Working Group (or an internal correspondence group) with the mandate to develop an overarching strategy on capacity building to that end. | The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Not started/little progress
| 109. Develops an overarching strategy for capacity building and assistance programs, which integrates the various existing capacity building initiatives. |  |  | Refer to STACFAD to undertake a review of its capacity building and assistance work and advise on how to improve it.
Total Quality Management Process | 126. The Panel recommends that ICCAT provides training in efficient chairing meetings to current Chairs and to new ones when they assume their duties. | STACFAD | S | Refer to STACFAD to consider and advise on options for aquiring such training and on financial aspects; the Secretariat should assist STACFAD in considering this matter as needed. | Option 1 = The Secretariat shall facilitate and organize bilateral meetings between outgoing/incoming chairs with a view to ensuring continuity of the works, efficiency and transfer of knowledge to the incoming Chairs. Option 2 = Whenever there is a new assignment or a change in current assignment of Chairs of ICCAT’s main and subsidiary bodies, the ICCAT Secretariat shall undertake to provide a two days training on procedural and substantive roles of the Chairs and in efficient chairing meetings to current Chairs and to new ones when they assume their duties. Option 3 = In order to avoid creating an additional workload on the Secretariat, outsource such task to an external training company. | The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Not started/little progress
Adequacy SRCS and Secretariat | 118. The Panel recommends that ICCAT evaluates the benefits of outsourcing its stock assessments to an external science provider while retaining the SCRS as a body to formulated the advice based on the stock assessments. | COM | M/L | For additional information, SCRS could advise on the pros and cons from a scientific perspective and STACFAD from a financial perspective. Commission to coordinate action among the bodies. | It was noted that the proposed changes on the current structure and functioning of SCRS would require further deliberations in future meetings of SCRS (2018 SCRS Report) | This item is primarily pending SCRS and COM action. The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Not started/little progress
Capacity Building Initiatives | 119. The Panel recommends that specific mentoring projects to include trainees in stock assessment teams be implemented. | SCRS | M/L | Refer to SCRS to advise on the merits of this idea and how it might be implemented effectively. STACFAD should assess any financial implications. | SCRS has conducted some training on stock assessment techniques in the past. | This item is primarily pending SCRS action. The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Progress/requires additional work.
Capacity Building Initiatives | 120. The Panel recommends that ICCAT develop specific mechanisms to ensure that more scientists with knowledge of the fisheries participate in stock assessment meetings and are directly involved in assessment teams. | SCRS | S/M | Refer to SCRS to advise CPCs/ Commission on key participants needed at science meetings and any other relevant matters. STACFAD should assess any financial implications. | It was noted that the proposed changes on the current structure and functioning of SCRS would require further deliberations in future meetings of SCRS. (2018 SCRS Report) | This item is primarily pending SCRS action. The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Not started/little progress
Capacity Building Initiatives | 121. The Panel also recommends that formal training in stock assessment be provided, possibly in cooperation with other organizations. | SCRS | M | Refer to SCRS to advise on the merits and how it might be implemented effectively. STACFAD should assess the financial implications. | Several sessions were organized by SCRS to improve the capacity in MSE processes with the involvement of external experts / in cooperation with other organizations at different times. The proposed changes on the current structure and functioning of SCRS would require further deliberations in future meetings of SCRS (2018 SCRS Report). | STACFAD needs to consider this recommendation at the 2018 Annual meeting though it is first pending SCRS action. | Progress/Requires additional work
SCRS Long-Term Strategy | 122.The Panel recommends that a process to formally incorporate scientific priorities with funding implications into the budget be implemented to fund the activities in the strategic plan. This could be achieved by a scientific research quota. | COM | S | Refer to the Commission to request that the Secretariat include relevant SCRS recommendations with financial implications in the draft biennial budget. SCRS should continue to prioritize its recommendations. STACFAD should consider and advise on any viable options to fund scientific priorities that cannot or should not be funded through the regular budget. | In 2017, the financing of SCRS was included in the regularization process of the Commission’s budget (Chapter 11 – Strategic Research Programme) and the new budget maintained the inclusion of the funds allocated for SCRS activities and of other expenses that had been financed through the Working Capital Fund. In 2015, SCRS recommended to develop a formal process to establish a scientific research quota to facilitate required research to improve the science. However, ICCAT has not yet approved such a fund. | The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Progress/Requires additional work.
Implementation Res 11-17 | 125. The Panel recommends that ICCAT considers adopting a system with scientists from external organisations, universities or otherwise are contracted to review SCRS assessments. | SCRS | S | Refer to SCRS to review and update the current TORs for these reviewers | A mechanism already exists for external reviewers to participate in SCRS stock assessments. | This recommendation is primarily pending SCRS action. | Progress to require additional work.
Financial and Administrative Issues | 127. The Panel recommends that a Working Capital Fund equivalent to 70% of the Annual Budget is prudent. This fund needs to be kept at that level in the interest of sound financial management. It should also be borne in mind that there are no guarantees that the costs of Annual meetings and scientific programmes etc., will continue to be financed by extra budgetary funds. | STACFAD | S | Refer to STACFAD to consider and advise on options. | The level of Working Capital Fund (WCF) has been set by ICCAT at 15% of the total annual budget. This level is now recommended by the Panel to be advanced to 70% of the Annual budget in the interest of a sound financial management. STACFAD needs to provide advice to the Commission for adoption of a more practical and realistic level of WCF. | The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Not started/little progress
Financial and Administrative Issues | 128. The Panel, taking account of the clear progress made by ICCAT in reducing outstanding debts on annual contributions by CPCs, recommends that ICCAT consider erasing CPCs debts for annual contributions outstanding for more than two years i.e. debts before 2015. This measure would alleviate the debt burden for certain Developing States. However, in parallel, ICCAT should amend its financial procedures and introduce an automatic sanction whereby, if the previous two years’ contributions have not been paid in full by the following Annual meeting, then the right to vote and be a quota holder is withdrawn for that CPC, until those debts are acquitted in full. | STACFAD | S | Refer to STACFAD to consider and advise on options. | Total amount due from pending contributions of Contracting Parties has reached to a level above 2 million Euros. Article X of the Convention and Rule 9 of ICCAT Rules of Procedure stipulates that the Commission may suspend the voting rights of any Contracting Party when its arrears of contributions equal or exceed the amount due from it for the two preceding years. | The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Not started/little progress
Financial and Administrative Issues | 129. The Panel also recommends that ICCAT consider cost recovery to finance key parts of their activities and thereby reduce the CPCs budgetary contributions and/or expand ICCAT’s activities (e.g. the High Seas Inspection Scheme). This cost recovery approach is based on the principle that the vessels of CPCs, which benefit from access to profitable fisheries, should share the financial burden for the science and monitoring programmes, which are crucial for the sustainability of those resources. An annual fee could be envisaged which would be paid per vessel of a certain size to ICCAT, via if necessary, the Flag CPC. | STACFAD | M/L | Refer to STACFAD to consider and advise on options. | STACFAD needs to decide on the draft proposed addition to ICCAT Financial Regulation 4 for an EBCD System Funding Scheme (STF-207/2018). Option 1 = The Secretariat with guidance from the STACFAD shall develop a Terms of Reference for establishment of an ad hoc Working Group (that may be considered in the form of an internal correspondence group) with the mandate to develop a cost-recovery policy towards a sustainable financial position at ICCAT. | The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Not started/little progress
Financial and Administrative Issues | 130. The Panel recommends, in line with good management practice, that ICCAT reviews every five years, through an independent human resources consultancy company, the staffing profile and workload of the Secretariat and, if necessary, adjust it to accurately reflect current and programmed workloads. In that review, the company should also review the staff assessment process. | STACFAD | S | Refer to STACFAD to consider and advise on financial and other considerations. Contracting process would be undertaken by the Secretariat | The nature of workload question in the Secretariat needs to be identified first. In this regard, ICCAT Secretariat has taken initiative to make a preliminary examination in the interim period, and contacted a few HRs consultancy companies to receive proposals for an independent review of the staffing profile, staff assessment process and workload of the Secretariat. | The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Progress/requires additional work.
Financial and Administrative Issues | 131. The Panel recommends that STACFAD be responsible for the terms of reference and the follow-up to the report of the consultancy. | STACFAD | M | Please refer to the above-cited observations |  | The STACFAD needs to consider this recommendation at the 2018 Annual meeting. | Progress/requires additional work.